## Slide 1
Infrastructure & Operations
Enterprise Database Services Roadmap
FY27–FY28 strategic direction, modernization priorities and dependencies
October 2026 | Draft for stakeholder validation
CONFIDENTIAL
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 2
Document Status
OVERVIEW
CONFIDENTIAL
2
Status
October 2026
Draft for stakeholder validation
Technology direction, sequencing and investment assumptions remain subject to validation.
Author & contributors
Author: Santhosh Kumar Chandrashekar, Enterprise Architecture
Contributors: Glen Loewen, Rakesh Nair and roadmap stakeholders
Review & endorsement
L1: Hani Mousa, Goran Zugic
L2: Charles Lewis, Joe Kitchen, Kaushik Venkatadri
Final endorsement follows closure of key roadmap decisions.
Sign-off conditions
NORTH demand and sequencing • Database decision matrix • DB2 disposition • ODS ownership • NFR and security ownership • Funding and delivery assumptions
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 3
Table of Contents
OVERVIEW
CONFIDENTIAL
3
01 Vision and outcomes
02 Strategic domains and principles
03 Current-state landscape
04 NORTH and program dependencies
05 Target-state direction
06 Database decision framework
07 Strategic initiatives and sequencing
08 Decisions and dependencies
09 Appendix
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 4
Advancing Enterprise Database Maturity
VISION
CONFIDENTIAL
4
Vision
Enable secure, resilient and cost-effective enterprise database services through governed workload placement, managed-service adoption, lifecycle modernization and consistent operational controls.
Accelerate time-to-market
Faster governed onboarding
Increase service resilience
Tiered recovery and testing
Strengthen security & compliance
Common controls and evidence
Enable data and AI workloads
Demand-led capabilities
Reduce operational effort
Managed services and automation
Emerging analytical and AI capabilities are enabled where demand, platform ownership, risk and cost are validated.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 5
Database Services Value Chain
STRATEGY
CONFIDENTIAL
5
PLAN
Classify workload and data
Apply decision matrix
Confirm SOR ownership
PROVISION
Approved service pattern
Policy-controlled onboarding
IaC / self-service
SECURE
RBAC and PAM
Encryption and audit
Residency and evidence
OPERATE
RTO/RPO tier
Monitoring, patching
Recovery testing
OPTIMIZE
Capacity and performance
TCO and licence exposure
Retirement savings
RETIRE
Exit and archival plan
Dependency validation
Licence reclamation
Key constituents: Database Product Owner • EA/Data Portfolio Architecture • DBA/Engineering • Application Owners • Security • IAM • Data Governance • FinOps • Compliance
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 6
I&O Guiding Principles
STRATEGY
CONFIDENTIAL
6
Managed services first
Prefer SaaS/PaaS where compatibility, residency, resilience, support and economics are validated.
Cloud appropriate
Select hosting based on workload and control requirements, not cloud preference alone.
Governed workload placement
Apply approved decision criteria before selecting an engine or service.
Automation everywhere
Provision, configure, patch and retire through repeatable automation.
Secure and resilient by design
Build service tiers, controls, evidence and recovery testing into every offering.
Value oriented
Balance velocity, resilience, experience, risk and total cost of ownership.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 7
Six Strategic Domains
STRATEGY
CONFIDENTIAL
7
F
Foundation
Decision framework, approved patterns, ownership and onboarding
S
Security
Controls, PAM, residency and evidence
G
Governance
Placement, exceptions, lifecycle and data-platform interlocks
P
Platform & Services
Modernization, ODS assessment and service tiers
C
Cost & Optimization
TCO, licensing and retirement economics
A
Automation
Provisioning lifecycle, policy-as-code and self-service
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 8
Strategic Focus Areas & Transformation Opportunities
STRATEGY
CONFIDENTIAL
8
1
Governed platform standardization
Decision matrix; service classifications; consistent intake
2
Migration and modernization
Managed-service adoption; Evergreen; migration vs modernization
3
Legacy disposition
DB2 inventory; eligible migrations; controlled exceptions
4
Resilience, security and compliance
Service tiers; RTO/RPO; HA/DR; minimum controls
5
Operating model and automation
Patterns; reference implementations; service readiness; self-service
AI-native, vector and graph capabilities remain demand-led assessments rather than automatic service commitments.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 9
Current State
Technology landscape, operational maturity and modernization constraints
CONFIDENTIAL
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 10
Enterprise Database Landscape
CURRENT STATE
CONFIDENTIAL
10
Platform | Current-state position | Roadmap implication
MS SQL Server | On-premises and cloud IaaS coexist with managed SQL services. | Managed services preferred, subject to compatibility, resilience, licensing and cost.
Oracle | 19c estate with Exadata services and lifecycle modernization opportunities. | Sequence modernization through Evergreen and approved service direction.
IBM DB2 | Long-standing containment with application and ETL dependencies. | Assess migration candidates, retained workloads and any new exception demand.
MongoDB / PostgreSQL | Existing use requires clearer service classification and operating ownership. | Define workload fit, support tier and onboarding through decision matrix.
ODS / specialized stores | Ownership and technology choices remain unresolved. | Resolve operational serving vs transactional state before technology selection.
Current deployment does not automatically constitute an approved enterprise placement pattern.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 11
Database Capability Maturity Framework
CURRENT STATE
CONFIDENTIAL
11
Platform standardization
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Lifecycle & technical debt
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Cloud / managed adoption
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Automation & self-service
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Resilience & DR
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Security & compliance
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Observability & operations
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Cost / FinOps
Evidence owner
Evidence source
Current score
Target score
Linked initiatives
Scores and supporting evidence must be validated with capability owners before the roadmap presents a maturity baseline or target.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 12
Alignment with the NORTH Data Platform / Data Strategy
DEPENDENCIES
CONFIDENTIAL
12
Confirmed boundary
Enterprise Database Services provides governed operational database capabilities and lifecycle services.
NORTH consumes and serves data through approved platform and integration patterns.
FY27–FY28 interlock
Validate database-service demand.
Define ODS and transactional-state ownership.
Confirm batch, streaming, API and CDC dependencies.
Validate Ab Initio / IDMC constraints.
Pending decisions
ODS technology and operating ownership
MDM, graph and vector boundaries
Approved capability sequencing
Business demand and funding
Roadmap completeness and sequencing remain dependent on validation of NORTH priorities, business demand, approved capabilities and Accenture-supported sequencing during Q4 2026–Q1 2027.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 13
From Current-State Insights to Future-Ready Focus Areas
CURRENT STATE
CONFIDENTIAL
13
MS SQL fragmentation
Managed-service modernization and governed exceptions
DB2 containment and dependencies
Strategic disposition and cross-program planning
Oracle lifecycle opportunity
Evergreen and evidence-based modernization
MongoDB / PostgreSQL service ambiguity
Service classification and placement guidance
ODS ownership unresolved
Decision matrix and data-strategy interlock
Ticket-driven provisioning
Operating model and automation
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 14
Target State
Confirmed direction, conditional capabilities and governed decisions
CONFIDENTIAL
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 15
Design Principles for Target State & Expected Outcomes
TARGET STATE
CONFIDENTIAL
15
Right service for the workload
Use data model, transaction pattern, availability, recovery, latency, scale, regulation, compatibility, support and TCO.
Resilient tiered architecture
Match RTO, RPO, HA, DR and recovery testing to workload criticality.
Security and governance by design
Use policy guardrails, privileged access, encryption, audit, residency and evidence.
Cost-transparent operations
Make licensing, consumption and managed-versus-self-managed economics visible.
Legacy disposition with controlled exceptions
Migrate eligible DB2 workloads and retain justified workloads only with support horizons and exit criteria.
Expected outcomes: cost efficiency • speed to value • reduced operational risk • controlled technical debt • evidence-based maturity uplift
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 16
Enterprise Database Landscape – Proposed Target State
TARGET STATE
CONFIDENTIAL
16
Platform | Confirmed direction | Conditional / pending
MS SQL Server | Managed services preferred over new self-managed cloud IaaS. | Placement across Azure SQL MI, AWS RDS and retained on-premises requires approved criteria.
Oracle | Exadata service direction and supported lifecycle management. | 26ai and Autonomous adoption depend on workload fit, business case and Evergreen sequencing.
IBM DB2 | Containment and strategic disposition. | Eligible transformation, application replacement or justified residual retention under exception.
MongoDB / PostgreSQL | Existing services remain candidates in the enterprise matrix. | Support tiers, workload fit and operating responsibilities require confirmation.
ODS / graph / vector | Assessment may begin as demand emerges. | Technology, ownership, risk and cost decisions remain open.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 17
High-Level Target Operating Model
TARGET STATE
CONFIDENTIAL
17
Consumers
Application teams • operational data consumers • analytics and BI • AI/ML workloads
Intake & decision
Workload classification • database decision matrix • service tier • architecture / exception decision
Database service layer
Approved relational, non-relational and specialized services with clear classifications
Automation, security & governance
Policy-as-code • RBAC/PAM • backup and DR • monitoring • evidence • cost controls
Foundation & operations
Cloud and on-premises platforms • service owner • runbooks • lifecycle • support model
Enterprise-ready services require ownership, support tiers, provisioning, controls, recovery, monitoring, lifecycle, cost model and operational runbooks.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 18
Work Packages & Sequencing
Decision enablement, platform readiness and modernization delivery
CONFIDENTIAL
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 19
Strategic Work Packages / Initiatives & Objectives
ROADMAP
CONFIDENTIAL
19
Code | Initiative | Rank | Objective
D1 | Enterprise database decision matrix | High | Placement criteria and technology classifications
D2 | NORTH and ODS database interlock | High | Demand, ownership and integration boundaries
D3 | Database NFR and security baseline | High | Service tiers, resilience and minimum controls
D4 | ARM database migrations | High | Move database components to approved cloud landing patterns
D5 | ARM database modernization | High | Modernize eligible IaaS databases to managed services
D6 | DB2 strategic disposition | High | Inventory and determine migrate, replace or retain paths
D7 | DBMS Evergreen and Oracle modernization | Medium | Lifecycle currency and evidence-based modernization
D8 | ETL / database modernization interlock | Medium | Ab Initio, CDC and IDMC dependency plan
D9 | Operating model and automation | Medium | Service readiness, patterns and self-service
D10 | AI-native capability assessment | Low | Demand-led vector and graph assessment
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 20
Work Packages / Initiatives Sequencing (2027–2028)
ROADMAP
CONFIDENTIAL
20
Workstream | Q4 2026–Q1 2027 | Q2 2027 | Q3–Q4 2027 | 2028
Decision framework | Define matrix and classifications | Approve criteria and exception process | Embed into intake and patterns | Review and optimize
NORTH / ODS interlock | Validate demand, ownership and sequencing | Approve boundaries and dependencies | Support prioritized platform demand | Reassess future demand
NFR / security baseline | Draft service tiers and controls | Approve owners and evidence | Implement across offerings | Measure compliance and recovery
DB2 disposition | Resolve CP4BA question; inventory estate | Approve waves and containment rules | Begin eligible transformations | Continue waves and track reduction
Modernization / Evergreen | Confirm dependencies and priorities | Plan managed-service and Oracle waves | Execute modernization | Continue delivery
Operating model / patterns | Identify gaps and readiness criteria | Prioritize patterns and automation | Deliver references and self-service | Expand automation
AI-native capability | Capture use cases only | Define discovery criteria | Assess funded demand | Decision-led adoption if justified
Delivery timing depends on business prioritization, funding, migration feasibility, application readiness and cross-program sequencing.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 21
Initiative Scope, Dependencies, Investment Status & Delivery Horizon
ROADMAP
CONFIDENTIAL
21
Initiative | Scope / technology | Investment status | Delivery horizon | Key dependency
ARM database migration & modernization | MS SQL, Oracle and related database components | Parent-program / confirm allocation | Extends beyond roadmap | Application readiness and landing patterns
DB2 strategic disposition | DB2 workloads and approved target services | To be assessed | Phased; extends beyond roadmap | Inventory, IBM validation, app and ETL compatibility
DBMS Evergreen / Oracle modernization | Supported database platforms | BAU plus project investment where required | Perpetual / sequenced waves | Vendor lifecycle and workload business case
ETL modernization interlock | Ab Initio, CDC, source DBs and IDMC | Program ownership to confirm | Decision and transition planning in 2027 | Compatibility and funded target architecture
NORTH / ODS demand | Operational serving and integration demand | NORTH allocation to confirm | Q4 2026–Q1 2027 validation | Business priority and ownership
Operating model & automation | Provisioning, monitoring, runbooks and self-service | I&O capacity and budget to confirm | 2027–2028 | Service owner and readiness backlog
Use consistent fields: funding status • internal effort • vendor investment • delivery horizon • confidence • dependencies.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 22
Assumptions, Dependencies & Decisions Before Sign-off
ROADMAP
CONFIDENTIAL
22
ID | Decision / input | Required output | Target | Status
D01 | NORTH interlock | Validated FY27/28 demand and caveats | Q4 2026 | Open
D02 | CP4BA DB2 on AWS | ADR with lifecycle and exit criteria | Near-term decision | Open
D03 | DB2 migration strategy | Workload inventory and phased plan | Q1 2027 | Open
D04 | ODS ownership | Approved pattern boundaries | Q1 2027 | Open
D05 | Ab Initio modernization | Architecture and transition dependencies | Q1 2027 | Open
D06 | ARM and Bill 64 | Demand estimates and funding confidence | Q1 2027 | Open
D07 | Service NFR and ownership | Service tier baseline and runbooks | Q2 2027 | Open
D08 | Target architecture sign-off | Governance and decision register | Q2 2027 | Open
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 23
Appendix
Decision criteria, detailed landscapes and assessment frameworks
CONFIDENTIAL
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 24
Capability Mapping – Validation Required
APPENDIX
CONFIDENTIAL
24
Retain this mapping in the appendix until it is validated against the authoritative Canada Life Technology Capability Model.
Use official L1–L3 TBM-aligned capability names; place Canada Life-specific service definitions only at the appropriate lower level.
Separate capabilities from service categories and technology products.
Map roadmap initiatives to approved capabilities after taxonomy validation.
Status
Capability hierarchy and service-category mapping are working content, not an approved taxonomy.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 25
Database Capability Maturity – Evidence Plan
APPENDIX
CONFIDENTIAL
25
Dimension | Evidence required | Owner | Linked roadmap initiative
Platform standardization | Approved patterns, estate split and exceptions | EA + I&O | Decision matrix
Lifecycle & technical debt | Version and containment inventory | DB Services | Evergreen / DB2 disposition
Managed-service adoption | Workload and platform inventory | I&O | ARM modernization
Automation & self-service | Provisioning and patching evidence | I&O Engineering | Operating model
Resilience & DR | Tier, test and recovery evidence | Support team | NFR baseline
Security & compliance | Control and evidence ownership | Security / IAM | Security baseline
Observability & operations | Monitoring and incident evidence | Operations | Operating model
Cost / FinOps | Licence and TCO evidence | FinOps | Cost validation
Do not publish precise current or target scores until evidence and capability-owner validation are complete.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 26
Enterprise Database Landscape – MS SQL Current State
APPENDIX
CONFIDENTIAL
26
On-premises dedicated VM clusters remain in use and are expected to persist beyond the roadmap horizon.
AWS includes self-managed SQL Server on EC2 and managed RDS services.
Azure includes SQL Server on VMs and Azure SQL managed-service options.
Existing deployment is not equivalent to approved future placement.
The decision matrix must consider compatibility, HA/DR, residency, licensing, cost and operational ownership.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 27
Enterprise Database Landscape – DB2, Oracle, MongoDB & PostgreSQL
APPENDIX
CONFIDENTIAL
27
IBM DB2
On-premises AIX/Linux estate plus an application-specific AWS deployment.
Contained platform with application and ETL dependencies.
Future demand requires explicit exception review.
Oracle
On-premises / Exadata estate with Azure direction.
19c lifecycle position is supported.
Future modernization must be sequenced through Evergreen and workload criteria.
MongoDB
Existing use requires validation of service, workload role, hosting and operating ownership.
Do not equate one current use case with the enterprise pattern.
PostgreSQL
AWS RDS PostgreSQL is in the landscape.
Placement, support tier and onboarding rules belong in the enterprise decision matrix.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 28
Enterprise Database Landscape – MS SQL Target Direction
APPENDIX
CONFIDENTIAL
28
Preferred direction
Use managed SQL services for eligible cloud workloads and avoid new self-managed cloud IaaS where a managed pattern meets requirements.
Placement outcomes
Azure SQL Managed Instance
AWS RDS for SQL Server
Retained on-premises patterns
Approved exceptions
Decision criteria
Compatibility
Availability and recovery
Residency and security
Licensing and TCO
Operational ownership
SQL Server 2025 should be shown as an Evergreen lifecycle direction subject to support, compatibility and delivery validation.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 29
Enterprise Database Landscape – Oracle Target Direction
APPENDIX
CONFIDENTIAL
29
Supported estate
Maintain supported 19c workloads where migration is not yet justified.
Service direction
Use approved Exadata services for qualifying Oracle workloads.
Lifecycle modernization
Assess 26ai through DBMS Evergreen based on compatibility, value, risk and cost.
Autonomous capability
Use only where workload fit and operating-model benefits are demonstrated.
DB2 transformation
Apply only to eligible applications; retain non-transformable workloads under controlled DB2 containment.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 30
High-Level Target Operating Model – Detailed View
APPENDIX
CONFIDENTIAL
30
1. Demand
Business and program requirements, criticality, data classification
2. Decide
Workload placement matrix, service classification and exception path
3. Provision
Approved pattern, automated onboarding, CMDB and ownership
4. Protect
RBAC/PAM, encryption, audit, residency, backup and DR tier
5. Operate
Monitoring, patching, runbooks, capacity and incident management
6. Optimize / retire
TCO, licence optimization, modernization and controlled decommissioning
Graph and vector capabilities remain conditional and demand-led; DB2 remains under strategic disposition rather than unconditional retirement.
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]

## Slide 31
Roadmap Priorities Summary
EXECUTIVE SUMMARY
CONFIDENTIAL
31
Priority | Rank | Pain point | Business impact | Domain
Enterprise database decision matrix | High | Inconsistent placement and service classifications | Governed intake and exceptions | Governance
NORTH / ODS database interlock | High | Unresolved ownership and demand | Avoid conflicting platform decisions | Platform & Services
Database NFR / security baseline | High | Inconsistent requirements and evidence | Resilience and compliance | Security
Managed-service modernization | High | Fragmented self-managed patterns | Lower operational overhead | Platform & Services
DB2 strategic disposition | High | Contained legacy estate and new demand | Controlled migration and risk | Cost & Optimization
Evergreen / Oracle modernization | Medium | Lifecycle modernization needs | Supportability and justified value | Platform & Services
Patterns and reference implementations | Medium | Missing implementation guidance | Repeatable delivery | Foundation
Operating-model automation | Medium | Ticket-driven provisioning | Faster service delivery | Automation
ETL / database interlocks | Medium | Compatibility may block change | Reduced migration risk | Governance
AI-native capability assessment | Low | Unvalidated demand | Avoid premature commitment | Platform & Services
Notes: [Sources] - Meeting transcript and Enterprise_Database_Roadmap_Changes_FY27_FY28.xlsx [/Sources]