## Roadmap Changes
FY27–FY28 Enterprise Database Services ¦ Proposed Roadmap Changes
Working change log from discussions; slides 1–22 of source deck not supplied. Slide 27–31 screenshots are context only, NOT verified slide 1–22 content.
Priority | Roadmap area | Proposed change / addition | Reason / discussion driver | Deliverable for roadmap | Proposed owner | Timing | Decision / dependency | Status
High | NORTH / data strategy interlock | Add explicit 2027–28 data-platform dependency and database-service demand assessment; do not imply business priorities are finalized. | NORTH priorities and Accenture sequencing remain subject to business validation. | Slide 11 interlock wording + dependency register | Data EA + NORTH + I&O | Q4 2026–Q1 2027 | Confirm programs, demand, and approved capability roadmap | Proposed
High | Database service catalog | Define which database engines are enterprise-supported, restricted, transitional, or exception-only; distinguish platform service from workload choice. | Need consistent intake and avoid treating isolated project requests as endorsed patterns. | Supported service matrix and exception criteria | I&O DB Services + EA | Q1 2027 | Review service owners and standards | Proposed
High | AWS RDS for DB2 / CP4BA | Resolve whether DB2 on AWS RDS is an approved service, a CP4BA-specific exception, or not supported; do not preapprove. | Working-group question conflicts with DB2 consolidation / retirement direction. | Decision record with business case, support horizon and exit plan | DB Services + CP4BA + EA | Q1 2027 | Validate vendor support, platform availability, cost, risk and DB2 roadmap | Open
High | DB2 strategic disposition | Show the distinction between legacy DB2 modernization, target database consolidation and exceptional retention. | DB2-to-Oracle transformation is being discussed alongside a new DB2 request. | Current/target matrix by workload; exception process | DB Services + application owners | Q1–Q2 2027 | Inventory DB2 workloads and modernization feasibility | Proposed
High | ODS and transactional persistence | Reference the existing NORTH ODS pattern 2.2; clarify operational serving versus transactional state and ownership before technology selection. | Sponsor onboarding / Wealth / Finance request low-latency and CRUD services. | NORTH ODS pattern coverage and database service selection criteria | Data EA + NORTH + I&O | Q1–Q2 2027 | Business use cases, SOR ownership, NFRs, support model | Proposed
High | NFRs, HA and DR | Add common requirements for RTO/RPO, HA topology, backups, replication, failover testing and monitoring to all service offerings. | Roadmap needs actionable resilience expectations rather than only engine names. | NFR baseline and service tiers | I&O DB Services + Security + EA | Q1–Q2 2027 | Existing NFR framework and current-state service levels | Proposed
High | Security / governance | Define RBAC, privileged access, encryption, patching, audit, data classification and regional residency guardrails across database services. | Global NORTH and European data scenarios require controls beyond hosting decisions. | Minimum control baseline with evidence owners | Security + IAM + Data Governance + I&O | Q1–Q2 2027 | Regional security sign-off and legal-entity controls | Proposed
Medium | SQL Server modernization | Validate managed service options, migration feasibility, licensing economics and exception rules; avoid declaring one target for every workload. | Database landscape direction includes SQL Server and cloud migration; sizing and application dependencies vary. | Workload placement decision tree | DB Services + application teams | Q2 2027 | Application compatibility, HA/DR, cost comparisons | Proposed
Medium | Oracle modernization | Document migration waves, Exadata service model, version lifecycle and actual rationale for DB2-to-Oracle conversions. | Oracle is positioned for larger/critical workloads in later-slide context; need economics and use-case fit. | Oracle migration criteria and lifecycle roadmap | DB Services + Oracle owners | Q2–Q3 2027 | Vendor support, licensing, performance, migration economics | Proposed
Medium | PostgreSQL / MongoDB | Confirm support tiers and when AWS RDS PostgreSQL or MongoDB are appropriate, including operational responsibilities. | Current landscape includes PostgreSQL and MongoDB; service ownership needs definition. | Service catalog entries and onboarding rules | I&O DB Services | Q2 2027 | Usage inventory, cost, security and support | Proposed
Medium | Ab Initio → IDMC dependencies | Identify database service impacts and timing of ETL modernization; avoid treating deferred 2028 review as approved plan. | Ab Initio migration and Informatica investment are explicit roadmap interlocks. | Dependency / transition milestone and decision | Data EA + ETL program + I&O | Q1–Q2 2027 | Approved modernization business case and timeline | Open
Medium | ARM / application modernization | Map ARM, Bill 64 and CP4BA database dependencies and modernization timing to platform roadmap. | Working-group message explicitly requests these program inputs. | Workload-to-service demand matrix | Portfolio EA + I&O + app owners | Q1–Q2 2027 | Program owners to validate scope, funding, dates | Open
Medium | Cost / licensing / FinOps | Add unit-cost, license exposure, managed-vs-self-managed TCO and retirement savings assumptions. | Business and I&O need a defensible cost case, not technology-only target state. | Cost model with assumptions and savings gates | I&O FinOps + Procurement + DB Services | Q2–Q3 2027 | Consumption, licenses, migration effort, DR cost | Proposed
Medium | Engineering patterns and catalog | Reuse approved EA pattern hierarchy and reference implementations; define database engineering design patterns and service catalog. | Existing pattern inventory and RACI should be leveraged rather than duplicated. | Pattern/service mapping with owners and readiness | EA + I&O Engineering | Q2–Q3 2027 | Approved pattern inventory, service offering RACI | Proposed
Medium | Capacity / operating model | Define provisioning, automation, runbooks, patching, backup, monitoring and support ownership for new database services. | I&O roadmap must cover operations as well as technology adoption. | Operating model, support tiers, automation backlog | I&O DB Services | Q2–Q4 2027 | Resourcing and operating budget | Proposed
Low | AI / vector / graph database | Treat AI-native, vector and graph capabilities as conditional options, not automatic enterprise service commitments. | Potential future AI needs require use-case, risk and cost validation. | Decision criteria / discovery backlog | AI EA + Data EA + I&O | Later / demand-led | Funded use case and platform ownership | Deferred

## Decisions and Inputs
Decisions & Inputs Needed Before Roadmap Sign-off
These are unresolved validation items, not final EA/I&O decisions.
ID | Decision / input | Question to resolve | Suggested participants | Target | Output required | Status
D01 | Slide 11 NORTH interlock | Which FY27/28 data strategy priorities are sufficiently validated to appear as committed roadmap demand? | NORTH / Data EA / I&O | Q4 2026 | Validated high-level demand and caveats | Open
D02 | CP4BA DB2 on AWS | Is AWS RDS for DB2 technically available/supported and, if so, strategic, limited exception, or rejected? | CP4BA / I&O / EA | Q1 2027 | ADR with lifecycle and exit criteria | Open
D03 | DB2 migration strategy | Which DB2 estates will remain, modernize, or convert to Oracle, and at what cost/risk? | App owners / DB Services | Q1 2027 | Workload inventory + phased plan | Open
D04 | ODS ownership | When is NORTH responsible for serving data versus hosting application transactional state? | NORTH / Data EA / I&O | Q1 2027 | Approved pattern boundaries | Open
D05 | Ab Initio modernization | What is the endorsed target and timing for IDMC migration and what is the dependency on database services? | ETL program / Data EA / I&O | Q1 2027 | Architecture and transition dependencies | Open
D06 | ARM and Bill 64 | What database service demand and funding are expected for modernization initiatives? | Portfolio EA / program leads | Q1 2027 | Demand estimates with confidence levels | Open
D07 | Service NFR and ownership | Which availability, recovery, monitoring and support tiers will I&O offer? | I&O / Security / EA | Q2 2027 | Service tier baseline and runbooks | Open
D08 | Target architecture sign-off | Who approves technology choices, exceptions and reference patterns under existing RACI? | EA / I&O / NORTH | Q2 2027 | Governance and decision register | Open